## Slide 1: IPO Process and Timeline
Kristoffer Skalmerud Jebsen and Solveig F. bugge

## Slide 2: Who does what and why?
IPO Process and Timeline
ListCo's financial adviser (optional)
IPO preparations, assistance with IPO execution
Managers' legal adviser
Legal IPO DD, legal adviser managers
Managers' financial adviser
Financial IPO DD, financial adviser managers
Owners
SteerCo and decision makers
Managers
Project management, marketing, bookbuilding, settlement
ListCo's communication adviser
Communication strategy, IR
ListCo's auditor
Audit and review of financial history
ListCo
Project leader, present to investors,
IPO execution
ListCo's legal adviser
IPO preparations, assistance with IPO execution

## Slide 3: Key workstreams and timeline // Oslo Børs/Euronext Expand
2022
May
Jun
Jul
Aug
Sep
Oct
Nov
OSE process
Public execution
Prospectus first filing
Early investor education
Early look meetings
Updated intro report
Listing application
Analyst presentation
Due diligence meeting
Marketing documents
PDIE
Transaction documents
Pilot fishing
First day of
trading (22 Oct)
Pricing
ITF
Financial history
Due diligence
IPO readiness
Bookbuilding/roadshow
Prospectus
Activity
Marketing process
VPS registration
Corporate resolutions
Intro report
Prospectus approval

## Slide 4: Key workstreams and timeline // Euronext Growth
2022
Aug
Sep
Oct
Nov
Submission of final draft
Marketing process
Financials
Marketing documents
Investor meetings
VPS registration
First day
of trading (22 Oct)
Cornerstone agreement
IPO readiness
Introductory report
Corporate resolutions
PDIE
Transaction documents
Public execution
Bookbuilding
Listing application
Information document
Activity
Pricing
ITF
OSE process
Submission of first draft
Due diligence
Analyst presentation
Early investor education

## Slide 5: Key workstreams and timeline // Oslo Børs/Euronext Expand
2022
May
Jun
Jul
Aug
Sep
Oct
Nov
OSE process
Public execution
Prospectus first filing
Early investor education
Early look meetings
Updated intro report
Listing application
Analyst presentation
Due diligence meeting
Marketing documents
PDIE
Transaction documents
Pilot fishing
First day of
trading (22 Oct)
Pricing
ITF
Financial history
Due diligence
IPO readiness
Bookbuilding/roadshow
Prospectus
Activity
Marketing process
VPS registration
Corporate resolutions
Intro report
Prospectus approval

## Slide 6: What characterises a good process?
IPO Process and Timeline
Project management
Ability to tackle challenges and identify pot holes early
Challenges will arise and the unexpected will happen
Planning, planning, planning
Identify key preparation areas early, front-load work to the extent possible
Open dialogue and information sharing
Experienced advisers who know each other - and have done this before
Good cooperation, clear communication and clear allocation of responsibilities
ListCo
Sufficient resources, clear allocation of responsibility, ownership to workstreams