## Sheet1
Priority | TEST Case | ETA | Main Topic | Functionality | Application | User Profile | Pre-requisites | Dependencies | References | Description | Expected Result | Testing status | Testing Comments | Last Day Execution | BUG Ref
Test relevance | Numerical ID of the test case | Planned date for completion | General topic object of the test case | Specific functionality of the test case | Application or module being tested | Type of client targeted by the test case | Conditions or setup needed before testing | Tests or systems that must be completed first | Related documents or requirements | Detailed description of the test case | Anticipated outcome of the test | Specify test outcome | Report notes / comments if needed | Specify test execution date | Identifier for any bugs found
High Priority | Connectivity_2 | 2026-07-31 | Connectivity | Environment configuration | MQ | Broker / Service Provider | Network access granted, IBM MQ licences installed |  |  | Configure the target IP address for IBM MQ connection (UAT: 212.107.65.1, PROD: 212.107.65.33, DR: 212.107.65.65) . | The MQ client resolves and targets the correct Euronext Securities Milan environment | To Do
High Priority | Connectivity_3 | 2026-07-31 | Connectivity | IP Address | MQ | Broker / Service Provider | MQ client configured with correct IP address |  |  | Check that communication between your system and Euronext opens correctly | Address set up correctly | To Do
High Priority | Connectivity_4 | 2026-07-31 | Security | Authentication | MQ | Broker / Service Provider | Confirm session established |  |  | Authenticate the MQ connection using public certificates by exchanging and validating public CA certificates between participant and Euronext | Authentication is successful, certificates are validated | To Do
High Priority | Connectivity_5 | 2026-07-31 | Messaging | Bidirectional communication | MQ | Broker / Service Provider | MQ connection authenticated |  |  | Verify bidirectional communication over IBM MQ by sending and receiving test messages in both directions | Messages are exchanged successfully in both directions | To Do
High Priority | Connectivity_6 | 2026-07-31 | Messaging | Queue management | MQ | Broker / Service Provider | Bidirectional communication established |  |  | Test queue management and guaranteed message delivery via IBM MQ sending a test message to the dedicated queue | Message is received by Euronext | To Do
High Priority | Connectivity_7 | 2026-07-31 | Resilience | Recovery | MQ | Broker / Service Provider | Queue management tested |  |  | Test recovery after connection interruption by simulating a network failure and restoring the MQ connection, then resending a message | Message delivery resumes without loss, transactional recovery is successfu | To Do
High Priority | Connectivity_8 | 2026-07-31 | Configuration | Channel setup | MQ | Broker / Service Provider | MQ client installed |  |  | Check that the technical settings for the communication channel are correct. This includes making sure the channel has the right name, type, and security settings. | Channel is created and visible in MQ Explorer or via command line with correct parameters. | To Do
High Priority | Connectivity_9 | 2026-07-31 | Security | Systems handshake | MQ | Broker / Service Provider | Channel configured in both system |  |  | Make sure that the secure connection between your system and Euronext works as expected. This involves checking that the security handshake (the process where both sides agree on how to protect the data) completes successfully and that the connection is protected. | System handshake completes successfully with no certificate errors and secure session is established | To Do
High Priority | Connectivity_10 | 2026-07-31 | Security | Encryption | MQ | Broker / Service Provider | System handshake successful |  |  | Verify message encryption in transit by sending a test message and capturing network traffic to confirm that the message is encrypted | Message content is encrypted and not readable in plain text during transmission over the network | To Do
High Priority | Connectivity_11 | 2026-07-31 | Messaging ISO20022 / 15022 | Message format | MQ | Broker / Service Provider | MQ connection established |  |  | Test message format compliance by sending a sample ISO 20022 message through MQ and verifying that it is accepted by Euronext | Message is accepted and processed by Euronext without format errors, confirming compliance with ISO 20022 | To Do
High Priority | Connectivity_12 | 2026-07-31 | Messaging ISO20022 / 15023 | Error handling | MQ | Broker / Service Provider | MQ connection established |  |  | Validate error handling for invalid messages by sending a malformed or non-compliant message and observing the error response | Error is returned, message is rejected with a clear error code and explanation provided by the system | To Do
High Priority | Connectivity_13 | 2026-07-31 | Resilience | Persistence | MQ | Broker / Service Provider | MQ connection established, persistent messages enabled |  |  | Test message persistence and delivery after MQ server restart by enabling persistent messages and restarting the server during transfer | No messages are lost, all persistent messages are delivered after server restart, confirming persistence settings | To Do
High Priority | Connectivity_14 | 2026-07-31 | Security | Access control | MQ | Broker / Service Provider | MQ connection established |  |  | Verify access control and authorisation for MQ queues by attempting to access a queue without proper permissions | Access is denied, and a security event is logged for the unauthorised attempt, confirming access control policies | To Do
High Priority | Connectivity_15 | 2026-07-31 | Monitoring | Alerting | MQ | Broker / Service Provider | MQ connection established |  |  | Test monitoring and alerting for MQ connection failures by simulating a connection issue and checking if alerting systems respond | Monitoring system detects the failure and sends an alert to the responsible team or monitoring dashboard | To Do
High Priority | Connectivity_16 | 2026-07-31 | Messaging | Sequencing | MQ | Broker / Service Provider | MQ connection established |  |  | Validate message sequencing and ordering by sending multiple messages in sequence and verifying their order at the destination | Messages are received in the correct order as sent, confirming sequencing and ordering functionality | To Do
High Priority | Connectivity_17 | 2026-07-31 | Messaging | Message size | MQ | Broker / Service Provider | MQ connection established |  | ISO 15022 | Test maximum message size handling by sending a message at the maximum allowed size and observing the system response | Message is accepted if within size limits, rejected if too large with appropriate error message | To Do
High Priority | Connectivity_18 | 2026-07-31 | Systems Configuration | Subscription | MQ | Broker / Service Provider | All systems are up and network connectivity is established |  | ISO 15022 | Confirm subscription for participant and MQ connectivity | Subscription active. | To Do
High Priority | Connectivity_19 | 2026-07-31 | Acquisition Flow 1 | MT540 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT540 (Receive Free) instruction. | Instructions accepted. | To Do
High Priority | Connectivity_20 | 2026-07-31 | Acquisition Flow 1 | MT541 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT541 (Receive AP). | Instructions accepted. | To Do
High Priority | Connectivity_21 | 2026-07-31 | Acquisition Flow 1 | MT542 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT542 (Deliver Free). | Instructions accepted. | To Do
High Priority | Connectivity_22 | 2026-07-31 | Acquisition Flow 1 | MT543 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT543 (Deliver AP). | Instructions accepted. | To Do
High Priority | Connectivity_23 | 2026-07-31 | Acquisition Flow 1 | MT548 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT548 outcome. | MT548 received with correct status. | To Do
High Priority | Connectivity_24 | 2026-07-31 | Push Information Flow 1 | MT548 status advice | MQ | Broker / Service Provider | Instructions processed in Acquisition Flow 1 |  | ISO 15022 | Generation MT548 (status advice). | Messages generated. | To Do
High Priority | Connectivity_25 | 2026-07-31 | Push Information Flow 1 | MT544/545/546/547 | MQ | Broker / Service Provider | Instructions processed in Acquisition Flow 1 |  | ISO 15022 | Generation MT544/545/546/547 (confirmations). | Messages generated. | To Do
High Priority | Connectivity_26 | 2026-07-31 | Push Information Flow 1 | Reception | MQ | Broker / Service Provider | Instructions processed in Acquisition Flow 1 |  | ISO 15022 | Confirmation to participant MQ. | Delivered to MQ. | To Do
High Priority | Connectivity_27 | 2026-07-31 | Acquisition Flow 2 | MT530 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT530 (Transaction Processing Command). | Instruction accepted. | To Do
High Priority | Connectivity_28 | 2026-07-31 | Acquisition Flow 2 | MT548 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT548 outcome. | MT548 received with correct status. | To Do
High Priority | Connectivity_29 | 2026-07-31 | Pull Information Flow 2 | MT549 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Send MT549 (Request for Statement/Status Advice). | Request accepted. | To Do
High Priority | Connectivity_30 | 2026-07-31 | Pull Information Flow 2 | MT548/MT586/MT537/MT536 | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Sends MT548 (status), MT586 (allegements), MT537 (pending), MT536 (transactions) as appropriate. | Correct messages generated. | To Do
High Priority | Connectivity_31 | 2026-07-31 | Pull Information Flow 2 | Reception | MQ | Broker / Service Provider | Participant is subscribed and authenticated |  | ISO 15022 | Confirmation to participant MQ. | Delivered to MQ. | To Do
High Priority | Connectivity_32 | 2026-07-31 | Scheduled Information Flow | MT537/MT536 | MQ | Broker / Service Provider | End of T2S settlement cycles |  | ISO 15022 | Generation MT537 (pending) and MT536 (transactions) at end of cycles. | Statements generated. | To Do
High Priority | Connectivity_33 | 2026-07-31 | Scheduled Information Flow | Reception | MQ | Broker / Service Provider | End of T2S settlement cycles |  | ISO 15022 | Confirmation to participant MQ. | Delivered to MQ. | To Do
High Priority | Connectivity_34 | 2026-07-31 | Scheduled Information Flow | Statement | MQ | Broker / Service Provider | End of T2S settlement cycles |  | ISO 15022 | Statement reception | Statements match settlement activity. | To Do
High Priority | Connectivity_35 | 2026-07-31 | Information Flow | MT578 | MQ | Broker / Service Provider | Settlement instruction is unmatched or requires allegement |  | ISO 15022 | Generation MT578 (Allegement Notification). | Allegement generated | To Do
High Priority | Connectivity_36 | 2026-07-31 | rewq<z1 | Reception | MQ | Broker / Service Provider | Settlement instruction is unmatched or requires allegement |  | ISO 15022 | Participant receives notification. | Notification matches pending instruction. | To Do
High Priority | Connectivity_37 | 2026-07-31 | Systems Configuration | Connectivity | MQ | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | Verify Participant DCP and connectivity performed. | DCP appears as active in Message Hub. | To Do
High Priority | Connectivity_38 | 2026-07-31 | Settlement Instruction Flow with Confirmations | sese.023.001. | MQ | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | DCP sends sese.023.001.XX (Settlement Instruction) via MQ. | Instruction is accepted by Message Hub. | To Do
High Priority | Connectivity_39 | 2026-07-31 | Settlement Instruction Flow with Confirmations | settlement status | MQ/T2S | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | T2S processes and sends settlement status (sese.024.001.XX or sese.025.001.XX) to X-TRM. | Status advice is generated. | To Do
High Priority | Connectivity_40 | 2026-07-31 | Settlement Instruction Flow with Confirmations | Status | MQ | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | ES-MIL delivers status to DCP via MQ. | DCP receives confirmation. | To Do
High Priority | Connectivity_41 | 2026-07-31 | Settlement Cancellation Flow | sese.027.001.xx | MQ | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | sese.027.001.xx (Cancellation Status Advice) received by es-mil and DCP | Cancellation status advice is generated. | To Do
High Priority | Connectivity_42 | 2026-07-31 | Modification & Allegement Removal Flow | sese.030.001.08 | MQ | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | DCP sends sese.030.001.08 (Modification Request) via MQ. | Modification request accepted. | To Do
High Priority | Connectivity_43 | 2026-07-31 | Modification & Allegement Removal Flow | sese.031.001.08 | MQ/T2S | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | T2S processes and sends sese.031.001.08 (Modification Status Advice) to ES-MIL and DCP | Modification status advice is generated. | To Do
High Priority | Connectivity_44 | 2026-07-31 | Modification & Allegement Removal Flow | sese.029.001.04 | MQ | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | For allegement, DCP sends sese.029.001.04 (Allegement Removal Advice) via MQ. | Allegement removal request accepted. | To Do
High Priority | Connectivity_45 | 2026-07-31 | Modification & Allegement Removal Flow | sese.028.001.08 | MQ/T2S | Broker / Service Provider | All systems are up and accessible. Participant DCP is registered. |  | ISO 20022 | T2S sends sese.028.001.08 (Allegement Notification) to ES-MIL and DCP. | Allegement notification received by DCP. | To Do
High Priority | Connectivity_46 | 2026-07-31 | Matching | Basic Matching (Equities) DFOP / RFOP | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; Matching rules active | Messaging | ISO 20022 (sese.023, sese.024); Matching rules | Instruct two legs via MQ using sese.023 (DFOP and RFOP). | 1) Instructions are received and acknowledged via sese.024; 2) Matching is successfully performed and both legs reach status 'MACH' (Matched); 3) Matching status is confirmed via sese.024. | To Do
High Priority | Connectivity_47 | 2026-07-31 | Full Settlement | Full Settlement (Equities) DFOP / RFOP | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; Sufficient securities; Matching rules active | Messaging | ISO 20022 (sese.023, sese.024, sese.025); Settlement lifecycle | Instruct two legs via MQ using sese.023; the client account must hold ≥ 100 units of the ISIN to trigger total settlement after matching. | 1) Instructions are received and acknowledged via sese.024; 2) Matching is successfully performed and both legs reach status 'MACH' (Matched); 3) Settlement engine executes full settlement for QTY=100; 4) Confirmation is received via sese.025 with status 'SETTD' (Settled); 5) Securities are debited from client and credited to esm. | To Do
High Priority | Connectivity_48 | 2026-07-31 | Unmatching | Unmatched Instruction (Single Leg – by design) | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; Matching rules active | Messaging | ISO 20022 (sese.023, sese.024); Matching exceptions | Instruct only one sese.023 (e.g. DFOP, QTY=100); do not submit the corresponding RFOP leg from esm. This simulates an unmatched scenario where only one side of the instruction is present in the system; no counterpart sese.023 is submitted. | 1) The instruction is received and acknowledged via sese.024; 2) Matching is not achieved; 3) The instruction remains in status 'UNMATCHED'. | To Do
High Priority | Connectivity_49 | 2026-07-31 | Pending / Failing | Pending Settlement (Hold Indicator / Insufficient Resources) | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; Matched instruction; insufficient securities or cash | Messaging | ISO 20022 (sese.023, sese.024); Settlement rules | Process a matched instruction with insufficient securities or cash available for settlement. | 1) The instruction is received and acknowledged via sese.024; 2) Matching is achieved (if applicable); 3) Settlement is not executed; 4) The instruction is set to status 'PENDING' (Pending). | To Do
High Priority | Connectivity_50 | 2026-07-31 | Partial Settlement | Partial Settlement (PARQ indicator – Quantity > Balance) | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; Insufficient balance; PartialSettlementIndicator enabled | Messaging | ISO 20022 (sese.023, sese.024, sese.025); Partial Settlement rules | Use the same two-leg structure (DFOP from client account, RFOP from esm account) with a quantity greater than the actual position on the security account. | 1) Instructions are received and acknowledged via sese.024; 2) Matching is successfully performed and both legs reach status 'MACH' (Matched); 3) Settlement engine executes settlement for the available quantity (e.g. QTY=60); 4) Confirmation is received via sese.025; 5) The remaining quantity stays in status 'PENDING'. | To Do
High Priority | Connectivity_51 | 2026-07-31 | Cancellation | Cancellation (Unmatched Instruction – sese.020) | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; Unmatched instruction exists | Messaging | ISO 20022 (sese.020, sese.027); Cancellation process | Send a sese.020 message to cancel an existing pending settlement instruction. | 1) The cancellation instruction (sese.020) is received and processed; 2) Cancellation is confirmed via sese.027 sent to the requester; 3) The instruction is updated to status 'CANCELLED'. | To Do
High Priority | Connectivity_52 | 2026-07-31 | Cross-CSD Settlement | Cross-CSD Settlement (Matching via PSET) | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; External CSD configured; PSET defined | Messaging | ISO 20022 (sese.023, sese.024, sese.025); Cross-CSD rules (PSET) | Send a settlement instruction with a different place of settlement (PSET). | 1) Instructions are received and acknowledged via sese.024; 2) Matching is successfully performed and both legs reach status 'MACH' (Matched); 3) Settlement engine executes full settlement for QTY=100; 4) Confirmation is received via sese.025 with status 'SETTD' (Settled); 5) Securities are debited from client and credited to esm. | To Do
High Priority | Connectivity_53 | 2026-07-31 | Error Handling (rejet ISO, doublon) | ISO Rejection / Duplicate Instruction | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; MQ validation active | Messaging | ISO 20022 (sese.023, sese.024); Validation rules | Send a malformed sese.023 via MQ (e.g. missing BusinessMessageHeader, invalid ISIN format, or mismatched quantity sign); verify that validation at the MQ gateway rejects the message before it reaches the matching engine. | 1) The message is rejected at gateway validation level; 2) The instruction is not processed further; 3) A rejection notification may be returned via sese.024 depending on system behavior. | To Do
High Priority | Connectivity_54 | 2026-07-31 | Hold /Release | Hold / Release (sese.023 on-hold and release via sese.030) | MQ / T2S | Broker / Service Provider | Systems available; Participant DCP registered; MQ connectivity established; Static data configured; MQ validation active | Messaging | ISO 20022 (sese.023, sese.024, sese.030); Hold/Release process | Send a sese.023 instruction via MQ with Hold indicator applied; release the instruction using sese.030. | 1) The instruction is received on-hold and acknowledged via sese.024; 2) The instruction remains in a pending state due to the hold condition; 3) The release instruction is processed via sese.030; 4) The instruction status is updated via sese.024 and becomes eligible for further processing. | To Do